## Project Plan
tType | tID | tDependency | tDependents | tStartConstrain | tEndConstrain | TIL | SS | TaskType | WBS | Task | Priority | Status | TaskLead | TaskLeadCost | BSD | BED | BD | ESD | EED | ED | PercentageCompleted | ASD | AED | AD | BCS | ECS | ACS | Notes | TColor | TPColor | BLColor | ACColor | LC | TimelineStart | [38 empty] | TimelineEnd
System | System | System | System | System | System | System | 1 | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System
[9 empty] | Construction - St. Louis Villa | [24 empty] | 43801 | 43802 | 43803 | 43804 | 43805 | 43806 | 43807 | 43808 | 43809 | 43810 | 43811 | 43812 | 43813 | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840
[9 empty] | Project Lead: Adam Smith | [24 empty] | 43801: W49; 43808: W50; 43815: W51; 43822: W52; 43829: W1; 43836: W2
[9 empty] | Project Budget: Estimated: $325,000.00 ¦ Baseline: $300,000.00 ¦ Task Costs: Estimated: $318,000.00 ¦ Baseline: $300,000.00 ¦ Actual: $178,150.00 | [24 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
tType | tID | tDependency | tDependents | tStartConstrain | tEndConstrain |  |  |  | WBS | Task Name | Priority | Status | Resource | Resource Cost | Baseline Start | Baseline End | Baseline Duration | Start | Finish | Duration | Percent Complete | Actual Start | Actual End Date | Actual Duration | Baseline Cost | Cost | Actual Cost | Notes | Bar Color | % Color | Baseline Color | Actuals Color |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
T | 1 |  |  |  |  | 0 |  |  | 1 | Architectural Design | NORMAL | Completed | Adam |  |  |  |  | 2019-12-02 | 2019-12-09 | 6 | 100% |  |  |  | 2500 | 2700 | 2850
T | 2 |  |  |  |  | 1 |  |  | 1.1 | Create draft of architecture | NORMAL | Completed | Adam |  |  |  |  | 2019-12-02 | 2019-12-04 | 3 | 100% |  |  |  | 2500 | 2700 | 2850 |  | cs | cs
T | 4 |  | 3¦ |  |  | 2 |  |  | 1.1.1 | Prepare construction documents | NORMAL | Completed | Matthew |  |  |  |  | 2019-12-02 | 2019-12-04 | 3 | 100% |  |  |  | 2500 | 2700 | 2850 |  |  | cs
T | 3 | 4_FS_0¦ | 6¦ | #NAME? |  | 1 |  |  | 1.2 | Agreement to architectural plan | NORMAL | Completed | Adam |  |  |  |  | 2019-12-05 | 2019-12-06 | 2 | 100% | [8 empty] | cs
M | 6 | 3_FS_0¦ | 9¦ | #NAME? |  | 1 |  |  | 1.3 | Sign agreement with Client | HIGH | Completed | Adam |  |  |  |  | 2019-12-09 | 2019-12-09 | 1 | 100% | [8 empty] | cs
T | 7 |  |  |  |  | 0 |  |  | 2 | Construction Phase | NORMAL | In Progress | Adam |  |  |  |  | 2019-12-10 | 2019-12-26 | 19 | 70% |  |  |  | 184500 | 201800 | 175300 |  | cs | cs
T | 8 |  |  |  |  | 1 |  |  | 2.1 | Foundation | NORMAL | Completed | Adrian |  |  |  |  | 2019-12-10 | 2019-12-17 | 8 | 100% |  |  |  | 66500 | 73800 | 73300 |  | cs | cs
T | 9 | 6_FS_0¦ | 10¦ | #NAME? |  | 2 |  |  | 2.1.1 | Excavation | NORMAL | Completed | Adrian |  |  |  |  | 2019-12-10 | 2019-12-13 | 4 | 100% |  |  |  | 32000 | 35000 | 31500 |  |  | cs
T | 10 | 9_FS_0¦ | 11¦ | #NAME? |  | 2 |  |  | 2.1.2 | Pour Concrete | NORMAL | Completed | Danny |  |  |  |  | 2019-12-16 | 2019-12-17 | 2 | 100% |  |  |  | 31000 | 35000 | 38000 |  |  | cs
T | 11 | 10_SS_0¦ | 13¦ | #NAME? |  | 2 |  |  | 2.1.3 | Level Concrete | NORMAL | Completed | Danny |  |  |  |  | 2019-12-16 | 2019-12-17 | 2 | 100% |  |  |  | 3500 | 3800 | 3800 |  |  | cs
T | 12 |  |  |  |  | 1 |  |  | 2.2 | Ground Floor | NORMAL | In Progress | Gary |  |  |  |  | 2019-12-18 | 2019-12-26 | 11 | 40% |  |  |  | 118000 | 128000 | 102000
T | 13 | 11_FS_0¦ | 19¦14¦ | #NAME? |  | 2 |  |  | 2.2.1 | Walls to 1st Floor | HIGH | In Progress | Gary |  |  |  |  | 2019-12-18 | 2019-12-23 | 4 | 80% |  |  |  | 57000 | 65000 | 60000
T | 19 | 13_FF_0¦ |  |  | #NAME? | 2 |  |  | 2.2.2 | Windows/ Doors | NORMAL | In Progress | Gary |  |  |  |  | 2019-12-18 | 2019-12-23 | 4 | 40% |  |  |  | 45000 | 47000 | 42000
T | 14 | 13_FS_0¦ | 16¦ | #NAME? |  | 2 |  |  | 2.2.3 | Roof structure | NORMAL | Planned | Toby |  |  |  |  | 2019-12-24 | 2019-12-26 | 3 | 0% |  |  |  | 16000 | 16000 |  |  | cs
T | 15 |  |  |  |  | 0 |  |  | 3 | Decoration Phase | NORMAL | Planned | Toby |  |  |  |  | 2019-12-27 | 2019-12-31 | 6 | 0% |  |  |  | 93000 | 93500
T | 16 | 14_FS_0¦ | 17¦ | #NAME? |  | 1 |  |  | 3.1 | Walls and Tiles | NORMAL | Planned | Gary |  |  |  |  | 2019-12-27 | 2019-12-31 | 3 | 0% |  |  |  | 13000 | 13500 |  |  | cs
T | 17 | 16_FF_0¦ | 18¦ |  | #NAME? | 1 |  |  | 3.2 | Interiors/ Furniture | LOW | Planned | Sara |  |  |  |  | 2019-12-27 | 2019-12-31 | 3 | 0% |  |  |  | 80000 | 80000 |  |  | cs
T | 18 | 17_FS_0¦ | 20¦ | #NAME? |  | 0 |  |  | 4 | Final touches | NORMAL | Planned | Adam |  |  |  |  | 2020-01-01 | 2020-01-02 | 2 | 0% |  |  |  | 20000 | 20000 |  |  | cs
M | 20 | 18_FS_0¦ |  | #NAME? |  | 0 |  |  | 5 | Move in with Family | NORMAL | Planned | Celine |  |  |  |  | 2020-01-03 | 2020-01-03 | 1 | 0% | [7 empty] | cs
Exported from Gantt Excel on 26-Dec-19 23:22:52
Note: This is a sample Gantt Chart created in Gantt Excel and exported to XLSX file format
December-2019
January-2020
2,700.00
2,700.00
2,700.00
201,800.00
73,800.00
35,000.00
35,000.00
3,800.00
128,000.00
65,000.00
47,000.00
16,000.00
93,500.00
13,500.00
80,000.00
20,000.00

## GS1 (hidden)
GCTYPE | SSN | DateFormat | WeekNumType | EC | CurrencySymbol | BaselineBudget | EstimatedBudget | ActualCosts | TotalACS | ShowOverdueBar | ShowBaselineBar | ShowActualBar | ShowCompleted | ShowInProgress | ShowPlanned | ShowLate | ShowTimelineGrid | ShowHolidays | ShowWeekends | ShowHolidaysPR | ShowWeekendsPR | ShowTodayLines | ShowDependencyConnector | ShowGrouping | ShowEstBaseBar | CurrentView | WeekStartDay | EnableBarText | BarTextCharacters | BarTextFontSize | BarTextDataColumnName | BarTextIsBold | BarTextIsItalic | BarTextIsUnderline | PercentageEntryMode | PercentageCalculationType | ProjectName | ThemeName | SelectedTheme | EBC | EMC | PCC | BBC | ABC | OBC | DLC | TLC | TBC | GBC | PBC | HBC | HC | WC | HCPR | WCPR | CR1C | CR12C | CR2C | CR3C | TGB | EBaseC | TPCH | TPCN | TPCL | TSCC | TSCI | TSCP | HCOL | DCOL | WCOL | MCOL | QCOL | HYCOL | YCOL | HWID | DWID | WWID | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | GRT | RefreshTimeline | TimelineVisible | CalcBED | CalcAED
ds082 | 0 | DDD DD\-MMM\-YY | ISO | TRUE | $ | 300000 | 325000 |  | 0 | FALSE | TRUE | TRUE | 1 | 1 | 1 | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 0 | 1 | D | 1 | TRUE | 20 | 10 |  | FALSE | FALSE | FALSE | manual | simple |  | Blue | Custom | [28 empty] | 240 | 39 | 5 | 1 | 1 | 1 | 1 | 3 | 2.5 | 6 | 8 | 10 | 12 | 15 | TRUE | TRUE | 2019-12-02 | 2020-01-10 | 6 | 10 | 12 | 15 | TRUE | TRUE | 2019-06-01 | 2019-07-26 | RS1 | TRUE | TRUE | TRUE | TRUE
Classic
Excel
Dark
Custom